## Sheet1
FDT Chassis Subsystem
| Current day: | 37
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57
[9 empty] | December | [13 empty] | January | [30 empty] | February
[9 empty] | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Num. | Task | Assigned | Predecessor | Start | End | Days | Act. End | % Done | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Tire data analysis | Robert
1.1 | Analyse 8psi cornering Hoosier18.0X6.0-10 | Robert |  | 1 | 15 | 15 | 16 | 100%
1.2 | Extract round 5 longitudinal data | Robert |  | 1 | 5 | 5 | 6 | 100%
1.3 | Extract round 6 cornering data | Robert |  | 6 | 10 | 5 | 12 | 100%
1.4 | Extract round 6 longitudinal data | Robert |  | 11 | 15 | 5 | 12 | 100%
1.5 | Analyse 8psi longitudinal Hoosier18.0X6.0-10 | Robert |  | 8 | 17 | 10 | 20 | 100%
1.6 | Analyse 8psi Hoosier18.0X7.5-10 | Robert |  | 11 | 20 | 10 | 31 | 100%
1.7 | Analyse 8psi Hoosier18.0X6.0-10LCO | Robert |  | 11 | 20 | 10 | 20 | 100%
1.8 | Choose tire | Robert |  | 21 | 21 | 1 | 31 | 100%
2 | Steady state model | Robert
2.1 | Geometry model | Robert |  | 21 | 28 | 8 |  | 0%
2.2 | Weight transfer model | Robert |  | 21 | 28 | 8 |  | 20%
2.3 | Calculate suspension forces | Robert |  | 29 | 36 | 8 |  | 0%
3 | Rear suspension and subframe | Robert
3.1 | Create suspension concepts | Robert |  | 1 | 15 | 15 |  | 100%
3.2 | Create subframe concepts | Robert |  | 1 | 15 | 15 | 25 | 100%
3.3 | Create combined concepts | Robert |  | 16 | 25 | 10 |  | 60%
3.4 | Analyse and optimize suspension geometry | Robert |  | 26 | 36 | 11 |  | 0%
3.5 | Design suspension linkage | Robert |  | 26 | 36 | 11 |  | 0%
3.6 | FEA of suspension linkages | Robert |  | 37 | 45 | 9 |  | 0%
3.7 | Choose rear axle components | Robert |  | 8 | 21 | 14 |  | 100%
3.8 | Design rear subframe | Robert |  | 26 | 41 | 16 |  | 40%
3.9 | FEA of rear subframe | Robert |  | 37 | 50 | 14 |  | 0%
3.10 | Design rear uprights | Kelton |  | 36 | 45 | 10 |  | 80%
3.11 | FEA rear upright | Kelton |  | 43 | 56 | 14 |  | 0%
4 | Frame | Grant
4.1 | Design frame layout | Grant |  | 1 | 28 | 28 |  | 75%
4.2 | Torsional rigidity analysis and bracing design | Grant |  | 36 | 56 | 21 |  | 0%
4.3 | Design harness mounts | Ross |  | 29 | 35 | 7 |  | 0%
4.4 | Design firewall and seat |  |  | 36 | 49 | 14 |  | 0%
4.5 | Design headrest | Grant |  | 22 | 28 | 7 |  | 0%
4.6 | Front bulkhead and impact attenuator |  |  | 29 | 35 | 7 |  | 0%
4.7 | Design tabs and mounts for everything | Grant |  | 36 | 56 | 21 |  | 0%
5 | Steering | Adam
5.1 | Steering force calculations | Adam |  | 1 | 20 | 20 |  | 30%
5.2 | Finalize steering geometry | Adam |  | 21 | 36 | 16 |  | 10%
5.3 | Steering column design/CAD | Adam |  | 1 | 14 | 14 |  | 25%
5.4 | Steering wheel design | Adam |  | 15 | 35 | 21 |  | 60%
5.5 | Design tie rods | Adam |  | 29 | 42 | 14 |  | 80%
5.6 | Steering system FEA | Adam |  | 37 | 56 | 20 |  | 0%
6 | Brakes | Tyler
6.1 | Brake system calculations | Tyler |  | 1 | 14 | 14 |  | 100%
6.2 | Finalize master cylinder and caliper choice | Tyler |  | 15 | 15 | 1 |  | 100%
6.3 | Design brake rotors | Tyler |  | 8 | 21 | 14 |  | 100%
6.4 | Model brake plumbing | Tyler |  | 29 | 42 | 14 |  | 0%
6.5 | Brake rotor FEA | Tyler |  | 21 | 35 | 15 |  | 0%
6.6 | Brake system thermal analysis | Tyler |  | 36 | 56 | 21 |  | 0%
7 | Pedals | Kelton
7.1 | Complete pedal box concepts | Kelton |  | 1 | 21 | 21 |  | 80%
7.2 | Detail design of pedals | Kelton |  | 22 | 35 | 14 |  | 60%
7.3 | Pedal FEA | Kelton |  | 36 | 49 | 14 |  | 0%
8 | Front suspension | Jacimar
8.1 | Analyse and optimize suspension geometry | Jacimar |  | 1 | 36 | 36 |  | 0%
8.2 | Design control arms | Robert |  | 15 | 25 | 11 |  | 50%
8.3 | FEA of control arms | Robert |  | 37 | 45 | 9 |  | 0%
8.4 | Spring rate and roll rate calculations | Jacimar |  | 8 | 21 | 14 |  | 0%
8.5 | Design bell cranks | Jacimar |  | 15 | 28 | 14 |  | 0%
8.6 | Design anti-roll bars | Jacimar |  | 22 | 35 | 14 |  | 0%
8.7 | FEA of bell cranks and anti-roll bars | Jacimar |  | 36 | 56 | 21 |  | 0%
8.8 | Bearing calculations | Ioana |  | 1 | 21 | 21 | 17 | 100%
8.9 | Finalize bearing choice | Ioana |  | 22 | 22 | 1 | 22 | 100%
8.10 | Initial front upright designs | Ioana |  | 8 | 35 | 28 |  | 50%
8.11 | Final front upright design | Ioana |  | 29 | 42 | 14 |  | 5%
8.12 | Front upright FEA | Ioana |  | 36 | 56 | 21 |  | 5%
8.13 | Spindle centerlock calculations | Ross |  | 1 | 21 | 21 |  | 60%
8.14 | Spindle concept designs | Ross |  | 8 | 35 | 28 |  | 40%
8.15 | Spindle FEA | Ross |  | 36 | 56 | 21 |  | 0%