## Sheet1
FDT Chassis Subsystem | [72 empty] | Design review for summer parts | [13 empty] | Manufacturing documents finished
| Current day: | 37
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104
[9 empty] | March | [12 empty] | April | [29 empty] | May | [30 empty] | June
[9 empty] | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Num. | Task | Assigned | Predecessor | Start | End | Days | Act. End | % Done | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Finish Design Work
1.1 | Frame
| Improve front frame strength - hard braking | Grant |  | 16 | 30 | 15 |  | 50%
| Improve torsional rigidity | Grant |  | 16 | 30 | 15 |  | 50%
| Initial design of front shock/ARB mount | Jacimar |  | 23 | 37 | 15 | 37 | 100%
| FEA and iterations of front shock/ARB mount | Jacimar |  | 37 | 58 | 22 |  | 0%
| Design suspension mount tabs | Grant |  | 30 | 44 | 15 |  | 0%
| FEA with front suspension tabs | Grant/Jacimar |  | 44 | 58 | 15 |  | 0%
| Harness mount tabs |  |  |  |  | 1 |  | 0%
| CAD of front bulkhead and IA |  |  |  |  | 1 |  | 0%
| Pedal mounts |  |  |  |  | 1 |  | 0%
| Head rest |  |  |  |  | 1 |  | 0%
| Update rear frame to engine |  |  |  |  | 1 |  | 0%
| Jacking point |  |  |  |  | 1 |  | 0%
1.2 | Suspension
| Front upright CAD assembly | Ioana |  | 2 | 16 | 15 |  | 90%
| Front spindle/upright FEA and iterations | Ioana/Ross |  | 16 | 44 | 29 |  | 25%
| Rear spindle/upright FEA and iterations | Kelton/Ross |  | 16 | 44 | 29 |  | 25%
| Front anti-roll bar initial design | Jacimar |  | 16 | 30 | 15 |  | 95%
| Front anti-roll bar FEA and iterations | Jacimar |  | 30 | 44 | 15 |  | 0%
| Front bellcrank FEA and iterations | Jacimar |  | 44 | 58 | 15 |  | 0%
| Linkage buckling calculations | Robert |  | 44 | 51 | 8 |  | 0%
| Rear anti-roll bar final design |  |  |  |  | 1 |  | 0%
1.3 | Steering
| Finalize front steering geometry | Adam |  | 9 | 23 | 15 |  | 50%
| Steering force calculations | Adam |  | 9 | 30 | 22 |  | 0%
| Design steering column mounts | Adam |  | 23 | 37 | 15 |  | 75%
| Steering column mount FEA and iterations | Adam |  | 37 | 58 | 22 |  | 0%
| Dashboard |  |  |  |  | 1 |  | 0%
1.4 | Wheels/Hubs
| Spindle CAD assemblies | Ross |  | 2 | 16 | 15 | 30 | 100%
1.5 | Brakes
| Brake rotor CAD - size/mounting | Tyler |  | 2 | 16 | 15 |  | 100%
| Brake rotor FEA and iterations | Tyler |  | 16 | 37 | 22 |  | 10%
| Brake rotor thermal analysis | Tyler |  | 23 | 37 | 15 |  | 10%
| Brake system plumbing diagram - fittings | Tyler |  | 37 | 58 | 22 |  | 0%
| Brake system routing CAD - plumbing/mounts | Tyler |  | 58 | 79 | 22 |  | 0%
1.6 | Pedals
| Pedal FEA and iteration | Kelton |  | 16 | 37 | 22 |  | 50%
| Pedal mount design | Kelton |  | 23 | 37 | 15 | 37 | 100%
| Pedal mount FEA and iteration | Kelton |  | 37 | 51 | 15 |  | 0%
1.7 | Miscellaneous
| Floorpan design |  |  |  |  | 1 |  | 0%
| Firewall initial design |  |  |  |  | 1 |  | 0%
| Fuel tank design |  |  |  |  | 1 |  | 0%
| Firewall FEA/seat design |  |  |  |  | 1 |  | 0%
| Wiring harness/electronics mounts |  |  |  |  | 1 |  | 0%
| Radiator mounts |  |  |  |  | 1 |  | 0%
| Body panel mounts |  |  |  |  | 1 |  | 0%
| Brake light |  |  |  |  | 1 |  | 0%
| Exhaust mounts |  |  |  |  | 1 |  | 0%
| Catch can mounts |  |  |  |  | 1 |  | 0%
| Aerodynamic mounts |  |  |  |  | 1 |  | 0%
2 | Manufacturing Preperation
2.1 | Frame
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
2.2 | Suspension
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
2.3 | Steering
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
2.4 | Wheels/Hubs
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
2.5 | Brakes
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
2.6 | Pedals
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
2.7 | Miscellaneous
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%
[6 empty] | 1 |  | 0%